## TestCase
Product Name |  | Games Bazar BD | TC Start Date |  | TC Execution Start Date | 14/09/2023 |  |  |  |  | TEST CASE
Module Name |  | Registration | TC End Date |  | TC Execution End Date | 16/09/2023 |  |  |  |  | PASS | 27
Epic |  |  | Test Case Developed By | Sagar Ghosh | Browser (tested) | yes |  |  |  |  | FAIL | 12
Developer Name (TL) |  |  | Test Case Reviewed By |  | Performance (tested) | No |  |  |  |  | Not Executed | 0
Test Executed by | [10 empty] | Out of Scope | 0
[11 empty] | TOTAL | 39
#SL | Module | Type of Testing | Features | Test Cases | Exepected Result | Actual Result | Test Data | Reproducing Steps | Bug Screen Shot | Dev Comments | Final Status | Remarks
1 |  | Browser Compatibility Testing |  | Check it by running in the google chorme browser | Run in chrome browser | as per expected | N/A | 1. Open google chrome 2.Search Games Bazar BD 3.Go to https://gamesbazarbd.com/ |  |  | Passed
2 |  |  |  | check it by running in the mozila firefox browser | Run in the firefox browser | not run in the browser | N/A | 1. Open mozila firefox 2.Seacrch Games Bazar BD 2.Go to https://gamesbazarbd.com/ | not responding in firefox |  | Failed
3 |  |  |  | check it by running in micrsoft edge browser | Run in the edge browser | not responded in the edge browser | N/A | 1.open microsoft edge browser 2.search games bazar BD 3.go to https://gamesbazarbd.com/ | not responding in edge |  | Failed
4 | User Registration | UI Testing | Sign Up | checking the spelling and grammatical mistake | no spelling and grammatical mistake | as per expected | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register butoon on top of the right corner 3.check the spelling and grammatical error |  |  | Passed
5 |  |  |  | checking the font,color and style | no missmatch are there and color,font,styles are ok | as per expected | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.check the font,color and style. |  |  | Passed
6 |  |  |  | checking the hovering the fields where its needed | hovers are presented there where its need | as per expected | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.check all fields that hovers are there or not |  |  | Passed
7 |  |  |  | checking the hover color are change | when take mouse in the hiver fields the button or field color will be changed | as per expected | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.check all fields with hovers that changes color the button or the fields. |  |  | Passed
8 |  |  |  | checking allignments of the fields | all fields allignment as per requirement | as per expected | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.checkallignment of the fields |  |  | Passed
9 |  | Functional Testing | Sign up | give all valid data in all field | should register appropiately | as per expected | all valid data | 1.go to https://gamesbazarbd.com/ 2.click on the register butoon on top of the right corner 3.fill up all fields with valid data 4.give tick on I agree to terms and condition 5.click on sign up button. |  |  | Passed
10 |  |  |  | Give numeric value in the name field | should give an error and give a pop up like "username can not be numeric numbers" | as not per expected | 1231 | 1.go to https://gamesbazarbd.com/ 2.click on the register butoon on top of the right corner 3.fill up the first name with na numeric value and all other fields are valid 4.give tick on I agree to terms and condition 5.click on sign up button. | invalid username |  | Failed
11 |  |  |  | keep blank the the name field | A pop up is shown below this field | as per expected | N/A | 1.go to https://gamesbazarbd.com/ 2.click on the register butoon on top of the right corner 3.ekep the name fileld blank and all other fields are valid 4.give tick on I agree to terms and condition |  |  | Passed
12 |  |  |  | give decimal value in the name field | should give an error and give a pop up like "invalid username" | as not per expected | 121.25552.132.100 | 1.go to https://gamesbazarbd.com/ 2.click on the register button on top of the right corner 3.fill up the first name with decimal value and all other fields are valid 4.give tick on I agree to terms and condition 5.click on sign up button. | decimal username |  | Failed
13 |  |  |  | give a invalid phonenumber | should give a popup or not taking this types of number to register | as not per expected | 0212112544111@ | 1.go to https://gamesbazarbd.com/ 2.click on the register button on top of the right corner 3.fill up all valid data without phone number and give a invalid phone number 4.give tick on I agree to terms and condition 5.click on sign up button. | invalid phonenumber |  | Failed
14 |  |  |  | keep blank the phonenumber | should give a popup "phone number is mandatory" | give a pop up "phone is not valid" | N/A | 1.go to https://gamesbazarbd.com/ 2.click on the register button on top of the right corner 3.fill up all valid data without phone number and keep the phone number field blank. 4.give tick on I agree to terms and condition | no pop up shown |  | Failed
15 |  |  |  | keep all the field blank and try to register | should not be registered | as per expected | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.keep all the field blank. 4.try to click sign up |  |  | Passed
16 |  |  |  | all the fields will be mandatory with a star mark or pop up | A red star will upright in the box or a pop up"this filed is mandoatory"wiil show when the box remain blank | no red star presented here and the pop up shows "this fiield is not valid" | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.keep all the field blank. 4.try to click sign up | mandatory and popup |  | Failed
17 |  |  |  | take all valid data except email address | A pop up is show"email is not valid" | as per expected | sag1bksjbd | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data except email field 4.give invalid mail address 5.try to click sign up |  |  | Passed
18 |  |  |  | take all valid data and take different types of mail address which are not belongs | A pop up will show "invalid email" | as not per expected | sag1bksjbd2@hmail.com | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data except email field 4.give invalid mail address 5.try to click sign up | invalid mail |  | Failed
19 |  |  |  | give a valid gmail id | successfully registered | as per expected | sag1bksjbd2@gmail.com | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data with a valid gmail in the email field 4.give invalid mail address 5.try to click sign up | valid gmail |  | Passed
20 |  |  |  | give a hotmail id | successfully registered | as per expected | sagar@hotmail.com | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data with a valid hotmail in the email field 4.give invalid mail address 5.try to click sign up |  |  | Passed
21 |  |  |  | give a yahoo mail | successfully registered | as per expected | faruk@yahoo.com | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data with a valid yahoo mail in the email field 4.give invalid mail address 5.try to click sign up |  |  | Passed
22 |  |  |  | give a mail id which are already taken previously | could not be registered and a meassge will show like "The email already has been taken." | as per expected | faruk@yahoo.com | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data with a valid mail in the email field which are previously used. 4.give invalid mail address 5.try to click sign up |  |  | Passed
23 |  |  |  | password and repeat password checking | without matching the both password field there will displayed an error and diplayed a mesage or pop up"Repeat Password is not valid." | as per expected | ps: 123456 repeat ps:123457 | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data with a valid password but a wrong password in the repeat password field. 4.click on the sign up button. |  |  | Passed
24 |  |  |  | minimum password length checking | password field should have a minimum character or digit | minimum six character needed | 123456 | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data with six digit password and confirm the same password. 4. click on sign up button. |  |  | Passed
25 |  |  |  | maximum password length checking | password field should have a maximum character or digit | as not per expected | 1111111111111111111111111111111111111111111111111111111111111111111111 | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data with unspecific digit password and confirm the same password. 4. click on sign up button. | maximum length password |  | Failed
26 |  |  |  | numeric value password checking | password should accept | as per expectation | &*()#$ | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data with numeric digit password and confirm the same password. 4. click on sign up button. |  |  | Passed
27 |  |  |  | checking password filed withnumeric,character and number | password should accept | as per expectation | ud121#$^ | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data with numeric,character and number together in the password and confirm the same password. 4. click on sign up button. |  |  | Passed
28 |  |  |  | an eye botton presented or not presented in the password filed | eye button presented | as per expectation | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data and verify that eye button is presented or not presented in password filed. 4. click on sign up button. |  |  | Passed
29 |  |  |  | when user click on the eye botton in the password field,the password are visible or not | password should visible in the field | as per expectation | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data 4.click on the eye booton in password field 5. click on sign up button. |  |  | Passed
30 |  |  |  | checkiing the checkbox field are working or not | checkbox should working | as per expectation | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data 4.click on the checkbox 5. click on sign up button. |  |  | Passed
31 |  |  |  | verifying the registration will done or not done without click the checkbox "I agree terms and condition" | should not not be registerted without accept tems and condition | registration completed | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data 4.not click on the checkbox of terms and condition. 5. click on sign up button. | checkbox checking |  | Failed
32 |  |  |  | terms and condition are present or not | when user click on terms and condition there wiil open a new tab and can show the terms and condition of the company | as per expected | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.give all valid data 4.click on the terms and condition. 5. click on sign up button. |  |  | Passed
33 |  |  |  | continue with google | successfully registered with google | as per expected | N/A | 1.go to https://gamesbazarbd.com/ 2..click on the register button on top of the right corner 3.click on continue with google. |  |  | Passed
34 |  | Functionality Testing | log in | log in with valid credentials which user have registered before | successfully log in | as per expected | email:sagarghosh1702074@gmail.com password: 123456 | 1.go to https://gamesbazarbd.com/ 2.click on the login button beseide the register button 3.give a mail and password which are previously registered . 4.click on the sign in button. |  |  | Passed
35 |  |  |  | log in with invalid credintials which are not registered before. | could not log in and error message or pop up shown here. | as per expected | email:sagar@gmail.com password: 123456 | 1.go to https://gamesbazarbd.com/ 2.click on the login button beside the register button 3.give a mail and password which are not previously registered . 4.click on the sign in button. |  |  | Passed
36 |  |  |  | wrong password verification | could not log in with wrong password | as per expected | 123458 | 1.go to https://gamesbazarbd.com/ 2.click on the login button beside the register button 3.give a right mail and wrong password. 4.click on the sign in button. |  |  | Passed
37 |  |  |  | remember password verification | when we logout and try to login again,the mail field and password field is filled up with automatically with the help of remerber me functionality. | as not per expected | N/A | 1.go to https://gamesbazarbd.com/ 2.click on the login button beside the register button 3.click on remember me 4.click on login 5.click logout button | remember me not working |  | Failed
38 |  |  |  | forget password functinality checking | give a mail to the registered email with some instructions hoe to recover password | as not per expected | N/A | 1.go to https://gamesbazarbd.com/ 2.click on the login button beside the register button 3.click on forget password 4.give the register mail 5.click on submit button | forget password not working |  | Failed
39 |  |  |  | continue with google | successfully login with googl account | as per expected | N/A | 1.go to https://gamesbazarbd.com/ 2.click on the login button beseide the register button 3.click on contue with google button. |  |  | Passed
40 |  |  | Improvement Scopes | Username can be case sensiitve,but there will no case sentivity.
41 |  |  |  | give a confirmation mail to the given mail address.
42 |  |  |  | "strong password" funtionality is recommended.
43 |  |  |  | give a forgot password field in the sign up/sign in page.
44 |  |  |  | password minimum length could be specified to the user end.
Negative test

## Report
Test Case Report
Project Name | Games Bazar BD
Module Name | Sign Up and Sign In |  |  |  |  | Total No. | Status | Result :
Test Case Version | [5 empty] | 27 | PASS
Written By | Sagar Kumer Ghosh |  |  |  |  | 12 | FAIL
Executed By | Sagar Kumer Ghosh |  |  |  |  | 0 | Not Executed | New Features | Testing Scope | Testing Environment : | Google Chrome Browser
Reviewed By | [5 empty] | 0 | Out of Scope
TEST EXECUTION REPORT
Test Case | PASS | FAIL | Not Executed | Out Of Scope | Total TC
| 27 | 12 | 0 | 0 | 39
Grand Total | 27 | 12 | 0 | 0 | 39
LIMITATIONS
Documents |  |  |  | Received | Useful
PRD |  |  |  | No | No
USER STORY |  |  |  | No | No
| Testing Type in Scope | Description
Yes/ No. Justification (If No): | Functional Testing | This type of testing ignores the internal parts and focuses only on the output to check if it is as per the requirement or not.
Yes/ No. Justification (If No): | Integration Testing | Testing of all integrated modules to verify the combined functionality after integration is termed as Integration Testing.
Yes/ No. Justification (If No): | Negative Testing | Testing having the mindset of “attitude to break” using incorrect data and invalid inputs.
Yes/ No. Justification (If No): | Usability Testing | Test application from user friendliness perspective.
Yes/ No. Justification (If No): | Browser Compatibility Testing | Browser Compatibility Testing is performed for web applications and it ensures that the software can run with the combination of different browser and operating system. This type of testing also validates whether web application runs on all versions of all browsers or not.
Yes/ No. Justification (If No): | Boundary Value Testing | There is an upper and lower boundary for each range and testing is performed on these boundary values.
Yes/ No. Justification (If No): | Risk Based Testing Or Regression Testing | Risk-Based Testing includes testing of highly critical functionality, which has the highest impact on business and in which the probability of failure is very high. Testing an application as a whole for the modification in any module or functionality is termed as Regression Testing.

## Test Metrics
Test Metrics
#SL | Metrics | Description | Result (%)
1 | Percentage of Test Cases Executed | (No. of Test Cases Executed / Total no. of Test Cases Written) * 100 | (39/39)*100 = 100
2 | Percentage of Test Cases Not Executed | (No. of Test Cases not Executed / Total no. of Test Cases Written) * 100 | (0/39)*100 = 0
3 | Percentage of Test Cases Passed | (No. of Test Cases Passed / Total no. of Test Cases Executed) * 100 | (27/39)*100 = 69.23
4 | Percentage of Test Cases Failed | (No. of Test Cases Failed / Total no. of Test Cases Executed) * 100 | (12/39)*100 = 30.77
5 | Percentage of Test Cases Blocked | (No. of Test Cases Blocked / Total no. of Test Cases Executed) * 100 | (0/39)*100 = 0
6 | Defect Density | No. of Defects found / Size (No. of Requirements) | N/A
7 | Defect Removal Efficiency (DRE) | (Fixed Defects / (Fixed Defects + Missed Defects)) * 100 | N/A
8 | Defect Leakage | (No. of Defects found in UAT/ No. of Defects found in Testing) * 100 | N/A
9 | Defect Rejection Ratio | (No. of Defects Rejected/ Total no. of Defects Raised) * 100 | N/A
10 | Defect Age | Fixed date - Reported date | N/A
11 | Customer Satisfaction | No. of complaints per Period of Time | N/A

## Bug Report (hidden)
Bug Reporting
# SL 43
Issue: Registered with invalid email address
Reproducing Steps:
1. Goto the URL https://www.bdshop.com/ 2. Click on Register button at the right corner 3. Fill all the fiels with invalid credentials 4.Click 'Create an Account'
Env: Production
Module: Sign Up
Severity: P1
Screenshot: Invalid email address error
Responsible QA: Tamanna Zubairi Sana